## Sheet1
Status of Roll-out Master Trainers Training - PMO action Item
Sl. No | States | Status of DRT/BRT | Target Agreed upon | Progress till 15th October
1 | Assam | Training started 11 SRP and 47 DRT trained. Empaneled 2520 BRTs to be trained. | 2016 | Next batch of remaining DRTs (78) will start end of Oct. | 78
|  |  |  | 523 BRPs training will start from 25th Oct. | 10230
|  |  |  | RP required for support. | 0
2 | Bihar | Have large number of community cadres. Profile entry not started. | 4000 | Data shared trained community cadres is 9138 and trained non-community cadre is 1092. A total of 10230 trained cadres available. | 89
3 | Chhattisgarh | Training started | 2000 | DRT completed. BRT training ongoing. | 6527
4 | Goa | Training started. | 110 | 42 SMT and 47 BRT trained. Total 89. | 0
5 | Gujarat | Training started. | 9900 | 1047 DMT and 5480 BMT are trained. Total 6527. | 0
6 | Himachal Pradesh | Plan has been finalized | 85 | Training in last week of September | 0
7 | Haryana | Plan is awaited | 400 | Training in last week of September | 600
8 | Jammu & Kashmir | Plan has been fixed | 800 | Training from first week of October | 203
9 | Jharkhand | 3 rounds of training completed | 1800 | 50 SRP and 550 BRPs trained. Total 600. | 0
10 | Karnataka | Revised Planning done | 500 | 203 BRT thematic training completed | 0
11 | Kerala | Have large number of Master Trainers. Profile Entry to be started | 2000 | Training from first week of October | 1540
12 | Madhya Pradesh | Training completed | 5800 | Training for the third batch in progress | 388
13 | Maharashtra | Training started | 3000 | 14+39 SMT, 50 DMT and 1414+23 BMT training completed. Total 1540 | 0
14 | Odisha | Training started. Plan to train 1084 initially. | 2350 | SRT 17, DRT 260, BRT 111, Total 388 trained. | 40
15 | Punjab | Plan is awaited | 150 | Training from first week of October | 0
16 | Pondicherry | Need MIS help to upload data | 40 | Completed | 0
17 | Rajasthan | Already have large pool of MT. Profile entry in process | 4742 | Training plan discussed and final plan awaited | 203
18 | Tamil Nadu | Need MIS help to upload data | 6000 | Data entry to begin | 1687
19 | UP | Plan finalized and shared. | 4000 | 203 trained and rest 303 will be trained by 28 Oct. | 0
20 | West Bengal | Plan finalized and shared. Plans to train 300 DRT and 2329 BRTs total 2629. | 4000 | 288 DRT and 1399 BRTs trained. Total 1687 | 0
21 | Uttarakhand | Training plan completed | 160 | Training from first week of October | 194
22 | Nagaland | 45 Staff have been trained as SRT/DRT. | 180 | Plan and module finalized. BRT training will start after funds are released from treasury | 0
23 | Tripura | SRPs and DRTs have been trained | 270 | 94 CSPs and 100 BRT training will complete by Dec | 0
24 | Mizoram | SRP trained. Modules for ToTs developed. | 50 | Modules finalized. BRT training will start end of Oct
25 | Meghalaya | SRP pool expanded and trained. | 160 | Modules finalized. BRT training will start in Nov-Dec
| Total |  | 54513 | 33830

## Sheet2
Assam | 78 | ANDHRA PRADESH | 0
Bihar | 10230 | ARUNACHAL PRADESH | 0
Chhattisgarh | 217 | ASSAM | 17
Goa | 89 | BIHAR | 0
Gujarat | 6527 | CHHATTISGARH | 217
Himachal Pradesh | 0 | GOA | 0
Haryana | 51 | GUJARAT | 696
Jammu & Kashmir | 21 | HARYANA | 51
Jharkhand | 600 | HIMACHAL PRADESH | 0
Karnataka | 203 | JAMMU AND KASHMIR | 21
Kerala | 256 | JHARKHAND | 0
Madhya Pradesh | 3209 | KARNATAKA | 191
Maharashtra | 1540 | KERALA | 256
Odisha | 388 | MADHYA PRADESH | 3209
Punjab | 56 | MAHARASHTRA | 194
Pondicherry | 40 | MANIPUR | 0
Rajasthan | 0 | MEGHALAYA | 7
Tamil Nadu | 6000 | MIZORAM | 1
UP | 203 | NAGALAND | 0
West Bengal | 1687 | ODISHA | 164
Uttarakhand | 4 | PONDICHERRY | 0
Nagaland | 0 | PUNJAB | 56
Tripura | 94 | RAJASTHAN | 0
Mizoram | 0 | SIKKIM | 0
Meghalaya | 7 | TAMIL NADU | 2851
Total | 31500 | TELANGANA | 0
|  | TRIPURA | 0
|  | UTTARAKHAND | 4
|  | UTTAR PRADESH | 53
|  | WEST BENGAL | 719

## Sheet3
| Total | SC | ST | Min | Sum
2014-03-31 | 21710992 | 4492898 | 2121098 | 1820440 | 8434436
2014-12-01 | 24189443 | 5184119 | 2474873 | 2036769 | 9695761
2015-12-01 | 29459630 | 6504015 | 3379635 | 2487743 | 12371393
2016-09-30 | 33608049 | 7245071 | 4460983 | 2823966 | 14530020
Month | Total HHs | SC | ST | Min | SC+ST+Min | %
Mar'14 | 21710992 | 4492898 | 2121098 | 1820440 | 8434436 | 38.85%
Dec'14 | 2478451 | 691221 | 353775 | 216329 | 1261325 | 50.89%
Dec'15 | 5270187 | 1319896 | 904762 | 450974 | 2675632 | 50.77%
Sep'16 | 4148419 | 741056 | 1081348 | 336223 | 2158627 | 52.03%